## High-Level Plan
Milestone Level | Task Name | Start | Finish | Who | 2023 | [6 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026
[5 empty] | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
| Key Dependencies | [41 empty] | Key Dependencies
| Ticketing |  |  |  | 2023 S: 2023-09-01; 2023 O: Ticketing Strategy; 2025 M: 2023-03-01; 2025 A: Tickets Released?
| Venues & Villages |  |  |  | 2025 M: 2023-03-22; 2025 A: Training Venues
| Games Family Demand Model |  |  |  | 2023 J: 2023-06-30; 2023 J: V1; 2023 S: 2023-09-30; 2023 O: V2; 2024 J: 2023-06-30; 2024 J: V3; 2025 J: 2023-06-30; 2025 J: V4
| Competition Schedules |  |  |  | 2023 O: 2023-10-31; 2023 N: Daily Comp Schedule; 2024 M: 2023-03-29; 2024 A: Sports Session Schedule; 2025 M: 2023-03-31; 2025 A: Sports Event Schedule
| Accomodation |  |  |  | 2023 O: 2023-10-31; 2023 N: Games Family Hotel Selected
| Games Workforce Demand |  |  |  | 2024 M: 2023-03-31; 2024 A: V1; 2024 D: 2023-12-31; 2025 J: V2; 2025 S: 2023-09-30; 2025 O: V3
| Service Levels |  |  |  | 2024 N: 2023-11-30; 2024 D: Target Service Levels (all client groups)
| Venue Operational Planning |  |  |  | 2023 J: VOP 1; 2024 M: VOP 2; 2025 M: VOP 3
Transport Capacity Analysis (TBD)
Transport Hubs (TBD)
Park n Ride Sites (TBD)
0 | TPD - Integrated Transport Planning and Delivery
0 | Strategic Planning & Legislation
1 | Transport Service Model Principles v1 Final | 2023-04-01 | 2023-06-30 | OC/DTP | 2023 J: 2023-06-30 |  | Draft competition schedule, venues, capacities, plans for each transport system and modelling outputs, CGF and Client groups surveyed and broad agreement reached
2 | Transport Client Service Levels v1 | 2024-03-01 | 2024-09-30 | OC | 2024 O: 2023-09-30
2 | Transport Client Service Levels Final | 2024-11-02 | 2025-06-30 | OC | 2025 J: 2023-06-30 |  | CGF agreement
1 | Games Transport Plan v1 | 2023-01-15 | 2023-06-30 | OC/DTP | 2023 J: 2023-06-30 |  | Draft competition schedule, venues, capacities, plans for each transport system and modelling outputs
2 | Games Transport Plan Final (DTP & OC) | 2024-04-01 | 2025-03-20 | OC/DTP | 2025 A: 2025-03-20 |  | Draft competition schedule, venues, capacities, plans for each transport system and modelling outputs
2 | Spectator & Workforce Transport Service Plan Phase 1 Vline by Corridor | 2023-05-06 | 2023-10-31 | DTP | 2023 N: 2023-10-31 |  | Draft competition schedule, venues, capacities, plans for each transport system and modelling outputs
2 | Spectator & Workforce Transport Service Plan Phase 2 - Vline network | 2023-11-01 | 2023-12-15 | DTP | 2024 J: 2023-12-15 |  | Draft competition schedule, venues, capacities, plans for each transport system and modelling outputs
2 | Spectator & Workforce Transport Service Plan Phase 3 - all other modes V1 | 2023-11-01 | 2023-12-15 | DTP | 2024 J: 2023-12-15 |  | Draft competition schedule, venues, capacities, plans for each transport system and modelling outputs
2 | Spectator & Workforce Transport Service Plan - all modes | 2024-02-01 | 2025-08-31 | DTP | 2025 S: 45169 |  | Final competition schedule, venues, capacities, plans for each transport system and modelling outputs
3 | Arrivals and Departures Transport Plan v1 | 2024-03-01 | 2024-11-01 | OC | 2024 D: 2023-11-01 |  | Draft competition schedule, accommodation plans and Welcome Centre plan, schedule of work for logistics, AAD and villages
2 | Arrivals and Departures Transport Plan Final | 2024-11-02 | 2025-06-30 | OC | 2025 J: 2023-06-30 |  | Final competition schedule, accommodation plans and Welcome Centre plan
3 | Ceremonies Transport Plan v1 | 2024-01-31 | 2024-05-31 | OC/DTP | 2024 J: 2023-05-31 |  | draft Ceremonies plans
2 | Ceremonies Transport Plan Final | 2024-06-16 | 2025-11-17 | OC/DTP | 2025 D: 2023-11-17 |  | Ceremonies operating plans complete with timings
3 | Kings Baton Relay Transport Plan v1 (may not be needed) | 2024-03-01 | 2024-11-01 | DTP/OC | 2024 D: 2023-11-01
2 | Kings Baton Relay Transport Plan Final (may not be needed) | 2024-11-02 | 2025-06-30 | DTP/OC | 2025 J: 2023-06-30
2 | Legislation to support Commonwealth Games | 2023-03-01 | 2024-06-30 | DTP/OC | 2024 J: 2023-06-30
2 | Accessible Transport Strategy | 2023-04-01 | 2023-09-30 | OC/DTP | 2023 D: 2023-11-30 |  | On-going updates to competition schedule, venues, capacities, ticket sales data and modelling output
2 | Transport Sustainability Strategy | 2023-06-26 | 2023-12-15 | OC/DTP | 2024 J: 2023-12-15
0 | Governance
2 | Transport Governance Review | 2024-04-30 | 2024-04-30 | OC | 2024 M: 2023-04-30
2 | Transport Governance Review | 2025-04-30 | 2025-04-30 | OC | 2025 M: 2023-04-30
2 | Annex 12 Issue Response (HCIR#86-Transport Infrastructure) | 2023-10-31 | 2023-10-31 | OC | 2023 N: 2023-10-31
2 | Annex 12 Issue Response (HCIR#89-Games Family Transport) | 2023-10-31 | 2023-10-31 | OC | 2023 N: 2023-10-31
2 | Annex 12 Issue Response (HCIR#90-Spectator & Workforce Transport) | 2023-10-31 | 2023-10-31 | DTP | 2023 N: 2023-10-31
2 | Annex 12 Issue Response (HCIR#91-Fleet rolling stock) | 2023-10-31 | 2023-10-31 | DTP | 2023 N: 2023-10-31
2 | Annex 12 Issue Response (HCIR#92-Accessible public transport options) | 2023-10-31 | 2023-10-31 | DTP | 2023 N: 2023-10-31
2 | Annex 12 Issue Response (HCIR#93-Free public transport) | 2023-10-31 | 2023-10-31 | DTP | 2023 N: 2023-10-31
2 | Annex 12 Issue Response (HCIR#94-Traffic Management Operations) | 2023-10-31 | 2023-10-31 | DTP | 2023 N: 2023-10-31
0 | Procurement
2 | Pipeline Review | N/A | N/A | OC/DTP | 2024 J: 2023-12-31; 2024 J: 2023-06-30; 2025 J: 2023-12-31; 2025 J: 2023-06-30
0 | Delivery Tools & Mechanisms
2 | Mapping Function | 2023-09-01 | 2025-09-30 | OC/DTP | 2025 S: 2025-09-30 |  | Six months before Games Time, maps to be completed
0 | Testing & Readiness
2 | Testing and Readiness Planning & Activities | 2024-06-15 | 2026-01-30 | OC/DTP | 2026 F: 2023-01-30 |  | Dependencies on Ingrid's team
3 | Policies & Procedures Drafted | 2025-01-30 | 2025-06-30 | OC/DTP | 2025 J: 2023-06-30
2 | Policies & Procedures Complete | 2025-07-01 | 2025-10-01 | OC/DTP | 2025 N: 2023-10-01
2 | Business Continuity Planning | 2024-07-01 | 2026-01-30 | OC/DTP | 2026 F: 2023-01-30
0 | C3
3 | Transport C3 Concept of Operations | 2024-06-30 | 2024-11-30 | UNKNOWN | 2024 D: 2023-11-30 |  | agreement with all key transport partners; Dependent on Ingrid's team
2 | Transport C3 Operations Plan | 2025-01-15 | 2025-08-10 | UNKNOWN | 2025 S: 2023-08-10 |  | Dependent on Ingrid's team
2 | TROC & TCC establishment | 2025-01-15 | 2026-01-31 | UNKNOWN
2 | Wayfinding and Signage | 2025-01-30 | 2026-01-30 | OC/DTP | 2026 F: 2023-01-30 |  | Dependencies with Overlay, with DTP re road network & PT, & R&R with DTP and partners
2 | Post Games Activities/Decommissioning | 2026-03-31 | 2026-06-30 | OC/DTP
0 | TBS - Bus Systems
0 | Procurement
1 | Bus Procurement (ROI) | 2023-05-22 | 2023-09-30 | DTP | [38 empty] | DTP metro bus recontracting in market 19 Jul 23 - Mar 24 | bar: 2023 J to 2023 J
2 | Bus RFT preparation | 2023-10-01 | 2024-03-28 | DTP | 2024 A: 2023-03-28
1 | RFT Released to Market | 2024-04-15 | 2024-05-31 | DTP | 2024 J: 2023-05-31
1 | Bus Provider(s) Appointed | 2024-09-14 | 2024-09-14 | DTP | 2024 O: 2023-09-14
1 | Bus and Coach contract operational | 2024-10-01 | 2026-06-15 | DTP | 2025 J: 2023-06-15
0 | Operations
3 | Bus Operations Plan v1 | 2023-11-01 | 2024-04-21 | DTP | 2024 M: 2023-04-21 |  | Draft output from Games Family Demand Model, session competittion schedule, confirmed venues and villages
3 | Bus Operations Plan v2 | 2024-04-22 | 2025-03-31 | DTP | 2025 A: 2023-03-21 |  | Draft output from Games Family Demand Model, session competittion schedule, confirmed venues and villages
3 | Bus Technology requirements confirmed | 2024-08-01 | 2024-12-20 | DTP | 2025 J: 2023-12-20 |  | Venues and accommodations finalised
3 | Bus Headcount requirements confirmed | 2024-10-01 | 2025-03-31 | DTP | 2025 A: 2023-03-31 |  | Venues and accommodations finalised
3 | Bus Overlay requirements confirmed | 2024-10-01 | 2025-03-31 | DTP | 2025 A: 2023-03-31 |  | Venues and accommodations finalised
3 | Bus FF&E requirements confirmed | 2025-01-02 | 2025-05-30 | DTP | 2025 J: 2023-05-30 |  | Venues and accommodations finalised
2 | Bus Operations Plan Final | 2025-03-22 | 2025-10-17 | DTP | 2025 N: 2023-10-17 |  | Venues and accommodations finalised
2 | Bus and Coach sub-contractors (incl buses, workers) confirmed | 2024-09-14 | 2024-09-14 | DTP | 2025 S: 45169
3 | Village Transport Mall draft drawings | 2023-07-01 | 2023-09-30 | OC | 2023 O: 2023-09-30 |  | Draft output from Games Family Demand Model, session competittion schedule, confirmed venues and villages
3 | Village Transport Mall Operations Plans (per Games City) v1 | 2024-06-30 | 2024-11-30 | DTP | 2024 D: 2023-11-30 |  | Draft output from Games Family Demand Model, session competittion schedule, confirmed venues and villages, bus operator in place
2 | Village Transport Mall Operations Plans (per Games City) Final | 2025-02-02 | 2025-11-30 | DTP | 2025 D: 2023-11-30 |  | Draft output from Games Family Demand Model, session competittion schedule, confirmed venues and villages, bus operator in place
0 | Depots
2 | Find and Procure Bus Depot Sites | 2024-04-01 | 2024-12-20 | DTP | 2025 J: 2023-12-20 |  | Venues and accommodations finalised
3 | Design depots v1 | 2024-06-01 | 2024-08-28 | DTP | 2024 S: 2023-08-28 |  | Depot site locations confirmed, venues and accommodations finalised
3 | Bus Depot Operations Plan v1 | 2024-08-01 | 2024-10-17 | DTP | 2024 N: 2023-10-17 |  | Depot site locations, venues and accommodations finalised
2 | Bus Depot Sites Lease Agreements signed | 2024-12-20 | 2024-12-20 | DTP | 2025 J: 2023-12-20 |  | Sufficient input from Legal and Land Agent
3 | Design bus depots Final | 2025-01-15 | 2025-06-30 | DTP | 2025 J: 2023-06-30 |  | Depot site locations confirmed, venues and accommodations finalised, bus operator in place
2 | Bus Depot Operations Plan Final | 2025-03-22 | 2025-10-17 | DTP | 2025 N: 2023-10-17 |  | Depot site locations, venues and accommodations finalised
2 | Install bus depot(s) overlay | 2025-10-01 | 2026-02-28 | DTP | [38 empty] | Depot designs complete | bar: 2025 N to 2026 F
1 | Operate bus depot(s) | 2025-11-28 | 2026-04-07 | DTP | 2026 M: 2023-04-07
0 | Post Games
2 | Bus Depot(s) site remediation | 2026-04-08 | 2026-06-30 | DTP | bar: 2026 A to 2026 J
2 | Bus and Coach contract closure | 2026-04-15 | 2026-07-31 | DTP | bar: 2026 A to 2026 J
0 | TFT - Fleet Services
0 | Procurement
2 | Electric Vehicle Requirements Agreed | 2023-04-01 | 2024-03-15 | OC | 2024 A: 2023-03-15 |  | Determination of EV charging infrastructure already available and planned investment by Government
2 | Fleet Principles | 2024-01-15 | 2024-04-30 | OC | 2024 M: 2023-04-30 |  | CGF agreement of T1 and T2 services being provided. Agreement on sites for road cycling events and the method of movement between cities. Team size calculator v1 complete
2 | Fleet Depot Sites License Agreements signed | 2024-01-15 | 2024-06-30 | OC | 2024 J: 2023-06-30 |  | Sufficient input from Legal and Land Agent
2 | Find and Procure Fleet Depot Sites | 2024-04-01 | 2024-12-20 | OC | 2025 J: 2024-12-20 |  | Venues and accommodations finalised
1 | Fleet Provider(s) procurement - Vehicles | 2024-04-01 | 2024-09-30 | OC | 2024 N: 2023-09-30 |  | Head of Fleet appointed
0 | Operations
3 | FTOP V1 | 2024-07-01 | 2024-10-31 | OC | 2024 N: 2023-10-31 |  | Venues and accommodations finalised, session competition schedule agreed
3 | Fleet Technology requirements confirmed | 2024-08-01 | 2024-12-20 | OC | 2025 J: 2023-12-20 |  | Venues and accommodations finalised
3 | Fleet Headcount requirements confirmed | 2024-10-01 | 2025-03-31 | OC | 2025 A: 2023-03-31 |  | Venues and accommodations finalised
3 | Fleet Overlay requirements confirmed | 2024-10-01 | 2025-03-31 | OC | 2025 A: 2023-03-31 |  | Venues and accommodations finalised
3 | Fleet Depot Operational Plan v1 | 2024-10-01 | 2025-03-21 | OC | 2025 A: 2023-03-21 |  | Depot site locations, venues and accommodations finalised
2 | FTOP Final | 2024-11-01 | 2025-09-30 | OC | 2025 S: 2023-09-30 |  | Venues and accommodations finalised, session competition schedule agreed
3 | Fleet FF&E requirements confirmed | 2025-01-02 | 2025-05-30 | OC | 2025 J: 2023-05-30 |  | Venues and accommodations finalised
2 | Fleet Depot Operational Plan Final | 2025-03-22 | 2025-08-17 | OC | 2025 S: 2023-08-17 |  | Depot site locations, venues and accommodations finalised
0 | Depots
3 | Design fleet depots | 2024-07-01 | 2025-03-21 | OC | 2025 A: 2023-03-21 |  | Depot site locations, venues and accommodations finalised
1 | Depot Operational | 2025-10-01 | 2026-04-30 | OC | 2026 M: 2023-04-30
3 | Install fleet depot(s) overlay | 2025-10-01 | 2026-02-28 | OC | [38 empty] | Depot site locations, venues and accommodations finalised | bar: 2025 O to 2026 F
0 | Workforce
3 | Driver Training Period | 2025-11-15 | 2026-02-28 | OC | bar: 2025 N to 2026 F
0 | Games Time
2 | Fleet Systems Games Time Operations | 2026-03-07 | 2026-04-01 | OC | 2026 A: 2023-04-01
0 | Post Games
2 | Commissioning and Decommissioning of Fleet Vehicles | 2025-11-01 | 2026-04-30 | OC | 2026 M: 2023-04-30 |  | Fleet depots operational
2 | Fleet Damage, Claims and Infringement close out | 2026-03-01 | 2026-06-30 | OC | [37 empty] | 2023-06-30 | bar: 2026 A to 2026 J
0 | TVT - Venue Transport
0 | Venues
2 | Venue Transport Overviews | 2023-05-01 | 2023-11-30 | OC | 2023 D: 2023-11-30 |  | Draft session competition schedule, venues confirmed and client capacities identified, client service overview for each transport system and initial modelling outputs, completion of VOP 1 session
2 | Games Cities Transport Overviews | 2023-05-01 | 2023-11-30 | DTP/OC/LGAs | 2023 D: 2023-11-30 |  | Draft session competition schedule, venues confirmed and client capacities identified, client service overview for each transport system and initial modelling outputs, completion of VOP 1 session
3 | Identify land requirements for TVT operations | 2023-04-01 | 2024-12-20 | OC | 2025 J: 2024-12-20 |  | Draft session competition schedule, venues confirmed and client capacities identified, client service overview for each transport system and initial modelling outputs, completion of VOP 1 session
3 | Find and Procure land for TVT operations | 2023-07-01 | 2025-06-30 | OC | 2025 J: 2023-06-30 |  | Venues and accommodations finalised, completion of VOP 2 session, completion of Venue Transport Strategies
3 | ​Local Area Traffic, Management and Parking (LATMP) Model Venue | 2024-04-01 | 2025-06-30 | DTP | [38 empty] | Venues and accommodations finalised, completion of VOP 2 session, completion of Venue Transport Strategies
3 | Venue Transport Technology requirements confirmed | 2024-08-01 | 2024-12-20 | OC | 2025 J: 2023-12-20 |  | Venues and accommodations finalised, completion of VOP2
3 | Venue Transport Headcount requirements confirmed | 2024-10-01 | 2025-03-31 | OC | 2025 A: 2023-03-31 |  | Venues and accommodations finalised
3 | Venue Transport Overlay requirements confirmed | 2024-10-01 | 2025-03-31 | OC | 2025 A: 2023-03-31 |  | Venues and accommodations finalised
3 | Venue Transport FF&E requirements confirmed | 2025-01-02 | 2025-05-30 | OC | 2025 J: 2023-05-30 |  | Venues and accommodations finalised
2 | Road Events transport plans V1 | 2024-10-01 | 2025-03-30 | OC | 2025 A: 2023-03-30 |  | Venues and accommodations finalised, completion of VOP 2 session, completion of Venue Transport Strategies, confirmation of routes for each race
2 | Road Events transport plans final | 2025-05-01 | 2025-11-30 | OC | 2025 D: 2025-11-30 |  | Venues and accommodations finalised, completion of VOP 3 session, completion of VTOP v1, confirmation of routes for each race
0 | Operations
2 | Venue Transport Operations Plan (VTOP) Model Venue | 2024-04-01 | 2024-06-30 | OC | 2024 J: 2023-06-30 |  | Venues and accommodations finalised, completion of VOP 2 session, completion of Venue Transport Strategies
2 | VTOP V1 | 2024-06-30 | 2024-11-30 | OC | 2024 D: 2023-11-30 |  | Venues and accommodations finalised, completion of VOP 2 session, completion of Venue Transport Strategies; aligns with LATMP plans
2 | VTOP Final | 2025-02-02 | 2025-11-30 | OC | 2025 D: 2023-11-30 |  | Venues and accommodations finalised, completion of VOP 3 session, completion of VTOP v1
2 | Games Cities TOP V1 | 2023-06-30 | 2023-12-15 | DTP/OC/LGAs | 2024 D: 2023-11-30 |  | Venues and accommodations finalised, completion of VOP 2 session, completion of Venue Transport Strategies, completion of Hub Transport Strategies
2 | Games Cities TOP V2 | 2024-06-30 | 2024-12-15 | DTP/OC/LGAs | 2024 D: 2023-11-30 |  | Venues and accommodations finalised, completion of VOP 2 session, completion of Venue Transport Strategies, completion of Hub Transport Strategies
2 | Games Cities TOP Final | 2025-02-02 | 2025-12-15 | DTP/OC/LGAs | 2025 D: 2023-11-30 |  | Venues and accommodations finalised, completion of VOP 3 session, completion of VTOP V1, completion of Hub TOP V1
0 | Vehicle Access & Parking
2 | LATMP V1 | 2024-06-30 | 2024-11-30 | DTP | 2024 D: 2023-11-30 |  | Venues and accommodations finalised, completion of VOP 2 session, completion of Venue Transport Strategies
2 | LATMP Final (DTP) | 2025-02-02 | 2025-11-30 | DTP | 2025 D: 2023-11-30 |  | Venues and accommodations finalised, completion of LATMP v1, VTOP V1, completion of VOP 3
3 | VAPPS Principles | 2024-06-30 | 2024-10-30 | OC | 2024 N: 2024-10-30 |  | VAPPS Manager appointed
3 | VAPPS Operations Plan | 2025-01-11 | 2025-06-30 | OC | 2025 A: 2023-06-30 |  | VAPPS Principles agreed
2 | VAPPS Delivery | 2025-11-30 | 2026-03-30 | OC | 2026 A: 2023-03-30 |  | Venues and accommodations finalised, VAPPS Operations Plan completed
0 | TSW - Spectator & Workforce
0 | Park and Ride/Walk
3 | PnR/W - concept of Operations draft | 2023-05-09 | 2023-07-21 | DTP | 2023 J: 2023-06-30
2 | Park and Ride/Walk Service Model V1 | 2023-05-01 | 2023-12-15 | DTP | 2024 J: 2023-12-20
2 | Park and Ride/Walk Service Plans V1 | 2023-05-01 | 2023-12-15 | DTP | 2024 J: 2023-12-20
3 | Spectator Demand Model Update and runs V1 | 2023-04-01 | 2023-09-30 | OC | 2023 O: 2023-09-30
3 | Spectator Demand Model Update and runs V2 | 2024-04-01 | 2024-06-30 | OC | 2024 O: 2023-06-30
3 | Spectator Demand Model Update and runs V3 | 2025-04-01 | 2025-06-30 | OC | 2025 J: 2023-06-30
2 | PnR/W - concept of Operations final | 2024-01-01 | 2024-07-31 | DTP | 2025 D: 2023-11-30
2 | Park and Ride/Walk Service Model final | 2024-05-31 | 2025-11-30 | DTP | 2025 D: 2023-11-30
2 | Park and Ride/Walk Service Plans final | 2024-05-31 | 2025-11-30 | DTP | 2025 D: 2023-11-30
0 | Site Identification
3 | Proposed Site List (V1) | 2023-07-14 | 2023-07-14 | DTP | 2023 A: 2023-07-14
2 | Proposed site list final (V2) | 2023-11-13 | 2023-11-13 | DTP | 2023 D: 2023-11-13
0 | Site access and control
3 | Agreement with Depts executed | 2023-08-04 | 2024-03-01 | DTP | 2024 A: 2023-03-01 |  | Site Identification
3 | Agreement with LGAs executed | 2023-08-04 | 2024-06-01 | DTP | 2024 J: 2023-06-01 |  | Site Identification
2 | All PnR/W sites contracted for use with owners | 2023-08-04 | 2024-12-15 | DTP | 2025 J: 2023-01-01 |  | Site Identification
0 | Procurement - Design and Civil Works
3 | PnR/W Market Engagement Strategy Approved | 2023-10-01 | 2024-01-31 | DTP | 2024 F: 2023-01-31 |  | Progressive as sites as confirmed and secured
1 | PnR/W RFT released to market | 2024-04-29 | 2024-05-24 | DTP | 2024 A: 2023-03-10
3 | PnR/W Engagement Approved | 2024-05-27 | 2024-06-21 | DTP | 2024 M: 2023-04-10
3 | PnR/W Contract executed | 2024-06-21 | 2024-06-30 | DTP | 2024 M: 2023-04-20
2 | PnR/W Contract commencement | 2024-07-01 | 2024-07-01 | DTP | bar: 2024 M to 2026 F; 2026 A to 2026 J
0 | Procurement - Operator (including booking application) | [41 empty] | Provides opportunity for input from the operator
3 | PnR/W Operator Market Engagement Strategy Approved | 2024-01-31 | 2024-01-31 | DTP | 2024 J: 2023-01-31
1 | PnR/W Operator RFT released to market | 2024-04-29 | 2024-05-24 | DTP | 2024 A: 2023-03-10
3 | PnR/W Operator Engagement Approved | 2024-05-27 | 2024-06-21 | DTP | 2024 M: 2023-04-10
3 | PnR/W Operator Contract executed | 2024-06-21 | 2024-06-30 | DTP | 2024 M: 2023-04-20
2 | PnR/W Operator Contract commencement | 2024-07-01 | 2024-07-01 | DTP | bar: 2024 M to 2026 F; 2026 A to 2026 J
0 | Civil Works
2 | Civil works | 2024-10-01 | 2025-10-31 | Contractor | 2025 N: 2023-10-31
2 | Booking Application Operational | 2024-04-01 | 2025-01-01 | Operator | 2025 F: 2023-01-01 |  | Ticketing strategy and will potentially need to be ready when tickets go on sale
0 | Transport Hubs
2 | Transport Hub Concept of Operations | 2023-10-01 | 2024-03-31 | DTP | 2024 A: 2023-03-31
2 | Transport Hub Service Model | 2023-10-01 | 2024-06-30 | DTP | 2024 A: 2023-06-30
2 | Transport Hub Service Plan | 2023-10-01 | 2024-06-30 | DTP | 2024 A: 2023-06-30
3 | Confirm Transport Hubs in games cities | 2023-03-31 | 2023-09-30 | DTP | 2023 O: 2023-09-30
3 | Identify Civil Works required | 2023-10-01 | 2024-06-30 | DTP | 2024 A: 2023-06-30
2 | Civil Works Delivery | 2025-01-01 | 2025-09-30 | DTP | 2025 O: 2023-09-30
3 | Operatoinal Requirments to Operators | 2024-01-01 | 2024-09-30 | DTP | 2024 O: 2023-09-30
2 | Agreement of Operational requirements | 2024-10-01 | 2024-12-31 | DTP | 2025 F: 2023-12-31
0 | Procurement - Civil Works at Transport Hubs
3 | Transport Hub Civil Works Market Engagement Strategy Approved | 2024-01-01 | 2024-06-30 | DTP | 2024 J: 2023-06-30
2 | Transport Hub Civil Works RFT released to market | 2024-07-15 | 2024-08-15 | DTP | 2024 S: 2023-09-01
3 | Transport Hub Civil Works Engagement Approved | 2024-08-16 | 2024-09-15 | DTP | 2024 O: 2023-09-15
3 | Transport Hub Civil Works Contract executed | 2024-09-30 | 2024-09-30 | DTP | 2024 O: 2023-09-30
2 | Transport Hub Civil Works Contract commencement | 2024-10-01 | 2024-10-01 | DTP | 2025 O: 2023-09-30
3 | Transport Hub Civil Works Contract conclude | 2025-09-30 | 2025-09-30 | DTP | 2025 O: 2023-09-30
0 | Active Transport
2 | Active Transport Strategy | 2023-10-01 | 2024-03-31 | DTP | 2024 A: 2023-03-31
3 | Active Transport Concept of Operations (part of SRN CoO) | 2023-06-01 | 2023-10-31 | DTP | 2024 A: 2023-06-30
| Sevice Models | 2023-07-01 | 2023-10-31 | bar: 2024 J to 2024 J
| Individual games city mapping | 2024-01-01 | 2024-06-30 | bar: 2024 J to 2024 J
3 | Identify Active Transport pathways (V1) | 2023-04-01 | 2023-12-31 | DTP | 2024 M: 2023-02-28
2 | Identify Active Transport pathways final (V2) | 2024-12-01 | 2025-02-28 | DTP | 2025 M: 2023-02-28
2 | Civil works for uplift - identify and deliver | 2024-01-01 | 2025-09-30 |  | 2025 O: 2023-09-30
0 | Public Transport
3 | Requirements to Service Providers - Regional Buses | 2024-01-01 | 2024-12-31 | DTP | 2026 F: 2023-01-31
3 | Requirements to Service Providers - Vline | 2024-01-01 | 2024-12-31 | DTP | 2026 F: 2023-01-31
3 | Requirements to Service Providers - Metro Buses | 2024-01-01 | 2024-12-31 | DTP | 2026 F: 2023-01-31
3 | Requirements to Service Providers - MTM | 2024-01-01 | 2024-12-31 | DTP | 2026 F: 2023-01-31
3 | Requirements to Service Providers - Yarra Trams | 2024-01-01 | 2024-12-31 | DTP | 2026 F: 2023-01-31
2 | Agreement of changes with Service Providers - Regional Buses | 2025-01-01 | 2025-06-30 | DTP | bar: 2025 J to 2026 F
2 | Agreement of changes with Service Providers - Vline | 2025-01-01 | 2025-06-30 | DTP | bar: 2025 J to 2026 F
2 | Agreement of changes with Service Providers - Metro Buses | 2025-01-01 | 2025-06-30 | DTP | bar: 2025 J to 2026 F
2 | Agreement of changes with Service Providers - MTM | 2025-01-01 | 2025-06-30 | DTP | bar: 2025 J to 2026 F
2 | Agreement of changes with Service Providers - Yarra Trams | 2025-01-01 | 2025-06-30 | DTP | bar: 2025 J to 2026 F
3 | Union engagement | 2024-07-01 | 2025-06-30 | Operator | 2025 J: 2023-06-30
3 | Service Provider Workforce Planning | 2024-07-01 | 2025-06-30 | Operator | 2025 J: 2023-06-30
3 | Funding Approvals | 2024-07-01 | 2025-06-30 | DTP | 2025 J: 2023-06-30
2 | Service changes commence | 2026-03-10 | 2026-03-31 | DTP | 2026 A: 2023-03-10
3 | Service changes conclude | 2026-03-31 | 2026-03-31 | DTP | 2026 A: 2023-03-10
0 | TRT - Road Network & Traffic Management
0 | GRN
3 | Games Route Network (GRN) Specification v2 | 2023-09-01 | 2023-11-30 | DTP | 2023 D: 2023-11-30
2 | GRN Concept of Operations | 2023-05-01 | 2023-10-31 | DTP | 2024 J: 45280
3 | GRN and highway network modelling/journey time modelling (V2) | 2023-12-01 | 2024-02-28 | DTP | 2024 M: 2023-02-28 |  | Depends on VOP and VTOP cycles
3 | GRN V2 | 2024-02-28 | 2024-02-28 | DTP | 2024 M: 2023-02-28 |  | Depends on VOP and VTOP cycles
3 | GRN and highway network modelling/journey time modelling (V3) | 2024-12-01 | 2025-02-28 | DTP | 2025 M: 2023-02-28 |  | Depends on VOP and VTOP cycles
3 | GRN V3 | 2025-02-28 | 2025-02-28 | DTP | 2025 M: 2023-02-28 |  | Depends on VOP and VTOP cycles
2 | GRN and highway network modelling/journey time modelling (V4 final) | 2025-12-01 | 2025-12-15 | DTP | 2026 J: 2023-12-15 |  | Depends on VOP and VTOP cycles
2 | GRN V4 (Final) | 2025-12-15 | 2025-12-15 | DTP | 2026 J: 2023-12-15 |  | Depends on VOP and VTOP cycles
0 | SRN
3 | Spectator Route Network (SRN) Specification v2 | 2023-09-01 | 2023-11-30 | DTP | 2023 D: 2023-11-30 |  | Depends on VOP and VTOP cycles
2 | SRN Strategy Concept of Operations | 2023-05-01 | 2023-10-31 | DTP | 2024 J: 2023-12-20 |  | Depends on VOP and VTOP cycles
3 | SRN and highway network modelling/journey time modelling (V2) | 2023-12-01 | 2024-02-28 | DTP | 2024 M: 2023-02-28 |  | Depends on VOP and VTOP cycles
3 | SRN V2 | 2024-02-28 | 2024-02-28 | DTP | 2024 M: 2023-02-28 |  | Depends on VOP and VTOP cycles
3 | SRN and highway network modelling/journey time modelling (V3) | 2024-12-01 | 2025-02-28 | DTP | 2025 M: 2023-02-28 |  | Depends on VOP and VTOP cycles
3 | SRN V3 | 2025-02-28 | 2025-02-28 | DTP | 2025 M: 2023-02-28 |  | Depends on VOP and VTOP cycles
2 | SRN and highway network modelling/journey time modelling (V4 final) | 2023-12-01 | 2025-12-15 | DTP | 2026 J: 2023-12-15
2 | SRN V4 (Final) | 2025-12-15 | 2025-12-15 | DTP | 2026 J: 2023-12-15
0 | LATMP
2 | Local Area Traffic Management and Parking (LATMP) Strategy | 2023-10-01 | 2024-03-31 | DTP | 2024 J: 2023-06-30
3 | LATMP Model Venue (DTP) | 2024-04-01 | 2024-06-30 | DTP | 2024 J: 2023-06-30
2 | LATMP Venues V1 | 2024-06-30 | 2024-11-30 | DTP | 2024 D: 2023-11-30
1 | LATMP Venues Final approved (DTP) | 2025-02-02 | 2025-11-30 | DTP | 2025 D: 2023-11-30
2 | Designated Walking Routes traffic management planning | 2024-02-01 | 2024-08-30 | DTP | 2024 S: 2023-08-31
0 | Procurement Design and Head Contract Operator
3 | LATMP Operator Market Engagement Strategy Approved | 2023-11-01 | 2024-04-30 | DTP | 2024 F: 2023-01-15
2 | LATMP Operator RFT released to market | 2024-07-01 | 2024-07-31 | DTP | 2024 M: 2023-02-28
3 | LATMP Operator Engagement Approved | 2024-08-01 | 2024-08-31 | DTP | 2024 A: 2023-03-31
3 | LATMP Operator Contract executed | 2024-09-01 | 2024-09-30 | DTP | 2024 M: 2023-04-15
2 | LATMP Operator Contract commencement | 2024-10-01 | 2024-10-01 | DTP | 2024 M: 2023-04-26
3 | LATMP contract concludes | 2026-06-30 | 2026-06-30 | DTP
3 | LATMP requirements gathering V1 | 2023-12-01 | 2023-12-15 | DTP | 2024 J: 2023-12-15 |  | requirements from all sites and routes that will have TMP
3 | LATMP requirements gathering V2 | 2024-12-01 | 2024-12-15 | DTP | 2025 J: 2023-12-15 |  | requirements from all sites and routes that will have TMP
2 | LATMP requirements gathering V3 | 2025-12-01 | 2025-12-15 | DTP | 2026 J: 2023-12-15 |  | requirements from all sites and routes that will have TMP
2 | Permit approvals received - pre games times | 2023-09-01 | 2026-03-09 | DTP | bar: 2025 D
2 | Permit approval process - live changes during games times | 2023-09-01 | 2026-03-31 | DTP
0 | TCE - Comms & Engagement
roles and responsibilities
establish WG - TCE (done)
establish WG - Spectator & Workforce transport experience
2 | Transport C&E Strategy | 2023-04-01 | 2023-12-15 | DTP | 2024 J: 2023-12-20
1 | Public-facing Games Transport Plan - Draft for Engagement | 2024-02-01 | 2024-03-30 | OC/DTP | 2024 M: 2024-03-30 |  | Draft competition schedule, venues, capacities, plans for each transport system and modelling outputs
1 | Public-facing Games Transport Plan - Final (released to public) | 2025-02-01 | 2025-03-30 | OC/DTP | 2025 A: 2025-03-30 |  | Final competition schedule, venues, capacities, plans for each transport system and modelling outputs
2 | Travel Demand Management Strategy | 2024-01-01 | 2024-06-30 | DTP/OC/LGAs
2 | Journey Planner Strategy | 2023-08-01 | 2023-12-15 | DTP/OC
3 | Spectator and Community Engagement | 2024-01-01 | 2026-06-30 | DTP/OC/LGAs | bar: 2024 J to 2026 F
3 | Business and Industry Engagement | 2024-01-01 | 2026-06-30 | DTP/OC/LGAs | bar: 2024 J to 2026 F; 2026 A to 2026 J
3 | Freight Industry Engagement | 2024-01-01 | 2026-06-30 | DTP/OC/LGAs | bar: 2024 J to 2026 F; 2026 A to 2026 J
3 | LAPPS Planning and process implementation | 2025-01-01 | 2025-12-31 | DTP/OC/LGAs | 2026 J: 2023-12-31
0 | Journey Planner
0 | Procurement
3 | Market Engagement Plan | 2024-01-01 | 2024-06-01 | DTP | 2024 J: 2023-06-01
2 | Journey Planner RFT in market | 2024-06-01 | 2024-06-30 | DTP | 2024 J: 2023-06-30
3 | Journey Planner provider(s) approved | 2024-07-22 | 2024-07-22 | DTP | 2024 A: 2023-07-22
3 | Contract Executed | 2024-07-31 | 2024-07-31 | DTP | 2024 A: 2023-07-31
2 | Contract Commences | 2024-08-01 | 2024-08-01 | DTP | 2024 S: 2023-08-01
3 | Contract concludes | 2026-03-31 | 2026-03-31 | DTP | bar: 2026 M to 2026 J
3 | Design, Develop and Deliver | 2024-08-01 | 2025-08-31 | DTP | 2025 S: 2023-08-31
Note on B30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dates TBC - ceremonies plan dates not yet available
Note on D34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Seems late (Dec?); check with Angela
Note on B35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Find out from Ingrid - do we need to align to another accessibility strategy?
Note on D35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Aligns with VOP
Note on B52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Check against what Ingrid has (program plan) before we put this in
Note on B55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AG - I think we should do this much earlier and review yearly and have a Games Time BCP
Note on B56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Basic w/shop required; where does this align with the overall integrated planning piece? Do we need to put anything in yet?
Note on D57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Seems late - check with Angela; also dependent on the work Ingrid's team will do
Note on B59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If we could build this by Nov 2025, it could be used over the summer
Note on B60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From comms & engagement strategy? Reply: Not for entry into SmartSheet at this stage
Note on D64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reflects end of process and notification to parties based on go to market finished before Metro Bus EOI going out to market no earlier than 19 July.
Note on B121: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reply: Includes all comp venues & training venues, festival / live sites, GF hotel, villages
Note on B122: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Comes from VOP
Note on B123: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Service plans
Note on B126: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to do a session with DTP on how this will work - part of end of second VOP
Note on B127: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will come from FA owners
Note on B131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: May not need them
Note on B149: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Where do these fit with the other service model and plans? Check with Angela
Note on B151: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will need to work with other OC FA's
Note on B155: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will coincide with end of VOP 2 Reply: + end of VTOP final, VOP 3, LATMP final
Note on B156: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: end of VTOP final, VOP 3, LATMP final
Note on B164: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: David to check dates with Procurement Reply: Dates look early
Note on A166: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assume value > $1m
Note on B170: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dates look early
Note on A172: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assume value > $1m
Note on B178: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Needs to be ready for when tickets go on sale (although depends if it's a ballot)
Note on B181: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What's the difference between this and the plan? Reply: AG - I dont think we need a model if we have a concept of ops
Note on B182: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What does this need to align with? Civil works, overlay, LATMP, SRN
Note on B188: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pipeline has June 23 to market & 2 yr contract commencing Oct 23
Note on A190: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assume < $1m
Note on B198: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: L2?
Note on B199: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: L2?
Note on B200: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Already happening as part of VOP1 Reply: Will need to validate with councils
Note on D200: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If this is part of VOP 1, can this be done by Dec 23? Dependency on last mile
Note on B203: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a L1 milestone here re PT?
Note on B204: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AG - These will occur after the service models are agreed in 2023.
Note on B209: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AG - This will occur much earlier, in early 2024. to facilitate changes and operational readiness.
Note on B222: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AG - GRN and SRN Strategy - I think this should be a CoOps and delivered earlier. Perhaps in Oct 23 with the Service Plans
Note on B239: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AG - LATMP strategy is in advance of the market engagement. Reply: Can we align to GRN?
Note on B244: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: + signage - would the TMP provider do this? Four procurement aspects - TMP design, TMP delivery, signage delivery, permit approval process
Note on D253: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mid 2025, or tie in with end of VOP3?
Note on B272: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AG - This will be dependent on a JP strategy. When is that confirmed?

## DTP Reconciliation
|  |  | In SS Upload? | Comments
L1 | Games Transport Plan V1 | 2023-06-30 | Yes | None - correct
L1 | Parking Site Identification | 2023-12-31 | Yes | Final (V2) Park and Ride/Walk Proposed Site List' - high-level plan has this as L2, with end date 13/11?
L1 | CGF Approved GTP | 2023-12-31 | Yes | Final Games Transport Plan approved by CGF - high-level plan has this as L2, with end date 31/03/25?
L1 | Bus & Coach RFT Released to Market | 2024-03-31 | Yes | High-level plan has this being released 15/04
L1 | Public Facing GTP V1 | 2024-03-31 | Yes | None - correct
L1 | Bus Provider Appointed | 2024-09-30 | Yes | High-level plan has this as 14/09
L1 | GTP Final | 2025-03-31 | Yes | See line 14
L1 | Travel Demand Management Strategy | 2025-03-31 | Yes | High-level plan has this ending 30/06
L1 | Public Facing GTP Final | 2025-03-31 | Yes | None - correct
L1 | Transport Service Model Principles Final | 2025-06-30 | Yes | Transport Client Service Levels Final
L1 | PT Transport Franchise Agreements | 2025-09-30 | ? | Agreement of changes with service providers?
L1 | Traffic Management Suppliers Appointed | 2025-09-30 | ?
L1 | Ceremonies Transport Plan Final | 2025-11-30 | Yes | Has been entered as L1, should be L2. End date on high-level plan is 17/11
L1 | Hub Transport Plan Final | 2025-11-30 | Yes | Has been entered as L1, should be L2
L1 | VTOP Final | 2025-11-30 | Yes | Has been entered as L1, should be L2
L1 | Road Events Transport Plan Final | 2025-11-30 | Yes | Has been entered as L1, should be L2
|  |  | In SS Upload? | Comments
L2 | Bus EOI | 2023-06-30 | Yes | None - correct
L2 | Final Draft Transport Plan | 2023-06-30 | Yes | None - correct
L2 | Transport Service Model Principles V1 | 2023-06-30 | Yes | None - correct
L2 | Bus EOI & Shortlisting | 2023-07-31 | Yes | High-level plan has this finishing 30/09
L2 | Accessible Transport Strategy | 2023-09-30 | Yes | High-level plan has this finishing 30/11 to align with end of VOP
L2 | Spectator & Workforce Transport Service Plan V2 | 2023-10-31 | Yes | First phase only
L2 | Venue Transport Strategies | 2023-10-31 | Yes | Venue Transport Overviews, but end date is 30/11 to align with end of VOP
L2 | Ceremonies Transport Plan v1 | 2023-12-31 | Yes | should be L3? And end date 31/05/24?
L2 | Draft Regional Transport Plans | 2023-12-31 | ?
L2 | Games City Transport Strategies | 2023-12-31 | Yes | Games Cities Transport Overviews, but end date is 30/11 to align with end of VOP
L2 | Parking Site Identification and Strategy | 2023-12-31 | Yes | high-level plan has this ending 30/11; not sure what the strategy is?
L2 | Transport Comms & Engagement Strategy | 2023-12-31 | Yes | None - correct
L2 | Spectator & Workforce Shuttle Bus Strategy | 2023-12-31 | ?
L2 | LATMP Specs? | 2024-02-28 | ?
L2 | Bus RFT prep | 2024-03-31 | Yes | None - correct
L2 | GRN design v2 by Hub | 2024-03-31 | Yes | High-level plan has this finishing 28/02; should be L3, not L2
L2 | Parking Site & Management Services Procurement Planning | 2024-03-31 | Yes | High-level plan has released to market 28/02
L2 | First Public Facing Transport Plan | 2024-03-31 | Yes | This should be L1

## Deliverables Summary
Project | Name | Definition | Scope | Audience | Approval Process
TPD - Integrated Transport Planning and Delivery | Transport Service Model Principles
TPD - Integrated Transport Planning and Delivery | Transport Client Service Levels
TPD - Integrated Transport Planning and Delivery | Games Transport Plan
TPD - Integrated Transport Planning and Delivery | Spectator & Workforce Transport Service Plan | Whole of network transport service plan that defines the span of hours, frequency and stopping patterns for all PT modes (with the GRN, SRN and PnR/W strategy overlayed).
TPD - Integrated Transport Planning and Delivery | Arrivals and Departures Transport Plan
TPD - Integrated Transport Planning and Delivery | Ceremonies Transport Plan
TPD - Integrated Transport Planning and Delivery | Kings Baton Relay Transport Plan
TPD - Integrated Transport Planning and Delivery | Legislation to support Commonwealth Games
TPD - Integrated Transport Planning and Delivery | Accessible Transport Strategy
TPD - Integrated Transport Planning and Delivery | Transport Sustainaibility Strategy
TPD - Integrated Transport Planning and Delivery | Testing and Readiness Planning & Activities
TPD - Integrated Transport Planning and Delivery | Policies & Procedures
TPD - Integrated Transport Planning and Delivery | Business Continuity Planning
TPD - Integrated Transport Planning and Delivery | Transport C3 Concept of Operations
TPD - Integrated Transport Planning and Delivery | Transport C3 Operations Plan
TPD - Integrated Transport Planning and Delivery | TROC & TCC establishment
TVT - Venue Transport | Venue Transport Overviews
TVT - Venue Transport | Games Cities Transport Overviews
TFT - Fleet | Fleet Transport Operating Plan (FTOP)
Road Network & Traffic Management | LATMP
TSW - Spectator & Workforce | VAPPS Principles
TSW - Spectator & Workforce | Park and Ride/Walk Service Model
TSW - Spectator & Workforce | Park and Ride/Walk Service Plans
TBS - Bus Systems | Bus Operations Plan
TBS - Bus Systems | Village Transport Mall Operations Plans (per Games City)
TBS - Bus Systems | Bus Depot Operations Plan
TFT - Fleet | Fleet Principles
TFT - Fleet | Fleet Depot Operational Plan
TVT - Venue Transport | Road Events transport plans
Venue Transport Operations Plan (VTOP)
Games Cities TOP
PnR/W - concept of Operations
Park and Ride/Walk Service Model V1
Park and Ride/Walk Service Plans V1
Transport Hub Concept of Operations
Transport Hub Service Model
Transport Hub Service Plan
Active Transport Strategy
Active Transport Concept of Operations
Games Route Network (GRN) Specification v2
GRN Strategy Concept of Operations
Spectator Route Network (SRN) Specification v2
SRN Strategy Concept of Operations
Local Area Traffic Management and Parking (LATMP) Strategy
TCE - Comms & Engagement | Transport C&E Strategy
TCE - Comms & Engagement | Public-facing Games Transport Plan - Draft for Engagement
TCE - Comms & Engagement | Travel Demand Management Strategy
TCE - Comms & Engagement | Journey Planner Strategy
Note on B37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What's the difference between this and the plan? Reply: AG - I dont think we need a model if we have a concept of ops
Note on B38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What does this need to align with? Civil works, overlay, LATMP, SRN
Note on B42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AG - GRN and SRN Strategy - I think this should be a CoOps and delivered earlier. Perhaps in Oct 23 with the Service Plans

## Q3 & 4 Priorities
Level | Task | Start | End | Who
TPD - Integrated Transport Planning and Delivery
Strategic Planning & Legislation
1 | Transport Service Model Principles v1 Final | 2023-04-01 | 2023-06-30 | OC/DTP
| Syndication with client groups | 2023-07-01 | 2023-07-14 |  | Grace
| Finalisation | 2023-07-31 | 2023-07-31 |  | Grace
| Submit to exec group for approval via Client Policies | 2023-08-31 | 2023-08-31
1 | Games Transport Plan v1 | 2023-01-15 | 2023-06-30 | OC/DTP
| Approvals - > CGF - needs to go through OC Board - confirm dates |  |  |  | Grace?
OC exec - late June
2 | Games Transport Plan Final (DTP & OC) | 2024-04-01 | 2025-03-20 | OC/DTP
2 | Spectator & Workforce Transport Service Plan Phase 1 Vline by Corridor | 2023-05-06 | 2023-10-31 | DTP
2 | Spectator & Workforce Transport Service Plan Phase 2 - Vline network | 2023-11-01 | 2023-12-15 | DTP
3 | Ceremonies Transport Plan v1 | 2023-04-01 | 2023-12-15 | OC/DTP |  | check ceremonies milestones
2 | Legislation to support Commonwealth Games | 2023-05-01 | 2024-06-30 | DTP/OC
XX
XX
2 | Accessible Transport Strategy | 2023-07-01 | 2023-11-30 | OC/DTP
| End Sept? |  | 2023-09-28 |  | Allan
Alignment to another accessibility strategy?
2 | Transport Sustainaibility Strategy | 2023-06-26 | 2023-12-15 | OC/DTP
| Sustainability Paper - for Environmental Sustainability WG |  | 2023-07-27 |  | Allan
| Strategy draft |  | 2023-11-30
2 | Annex 12 Issue Response (HCIR#86-Transport Infrastructure) | 2023-10-31 | 2023-10-31 | OC
2 | Annex 12 Issue Response (HCIR#89-Games Family Transport) | 2023-10-31 | 2023-10-31 | OC
2 | Annex 12 Issue Response (HCIR#90-Spectator & Workforce Transport) | 2023-10-31 | 2023-10-31 | DTP
2 | Annex 12 Issue Response (HCIR#91-Fleet rolling stock) | 2023-10-31 | 2023-10-31 | DTP
2 | Annex 12 Issue Response (HCIR#92-Accessible public transport options) | 2023-10-31 | 2023-10-31 | DTP
2 | Annex 12 Issue Response (HCIR#93-Free public transport) | 2023-10-31 | 2023-10-31 | DTP
2 | Annex 12 Issue Response (HCIR#94-Traffic Management Operations) | 2023-10-31 | 2023-10-31 | DTP
Other
| Bus & Coach Op Delivery Model | 2023-06-19 | 2023-06-19 |  | Michael | We need to submit a paper in partnership with DTP on the Games Family Bus and Coach Management model, going to CEO Group on June 28th. Papers are due 19th June.
| Bendigo Modelling Process |  | 2023-08-31 |  | Michael
RASCI
Governance
| Risk w/shop | 2023-07-10 | 2023-07-10
| Risk register / risks in SmartSheet |  |  |  | Terri
| ‘What We Know’ - TPT action items | 2023-06-30 | 2023-06-30 |  | Allan, Michael
| Ccom - Nov | 2023-11-08 | 2023-11-10
Ministers Office update - GTP
| CGA Ref Group Update | July | July |  | Allan, Michael, Grace
CEO group
Board meetings
Delivery Tools & Mechanisms
2 | Mapping Function | 2023-09-01 | 2025-09-30 | OC/DTP
Testing & Readiness / C3
| Planning Session - prep | 2023-07-25 | 2023-07-25 |  | Allan
| Planning session - with DTP | TBD | TBD
TBS - Bus Systems
1 | Bus Procurement (ROI) | 2023-05-22 | 2023-09-30 | DTP
2 | Bus RFT preparation | 2023-10-01 | 2024-03-28 | DTP
3 | Bus Operations Plan v1 | 2023-11-01 | 2024-04-21 | DTP
3 | Village Transport Mall draft drawings | 2023-07-01 | 2023-09-30 | OC |  | Jacquie to check with Fiona Connor - when can we do this?
TFT - Fleet Services
2 | Electric Vehicle Requirements Agreed | 2023-08-01 | 2024-03-15 | OC
Sponsorship
TVT - Venue Transport
2 | Venue Transport Overviews | 2023-05-01 | 2023-11-30 | OC
2 | Games Cities Transport Overviews | 2023-05-01 | 2023-11-30 | DTP/OC/LGAs
3 | Identify land requirements for TVT operations | 2023-04-01 | 2024-12-20 | OC
3 | Find and Procure land for TVT operations | 2023-07-01 | 2025-06-30 | OC
TSW - Spectator & Workforce
3 | PnR/W - concept of Operations draft | 2023-05-09 | 2023-07-21 | DTP
2 | Park and Ride/Walk Service Model V1 | 2023-05-01 | 2023-12-20 | DTP
2 | Park and Ride/Walk Service Plans V1 | 2023-05-01 | 2023-12-20 | DTP
3 | Spectator Demand Model Update and runs V1 | 2023-04-01 | 2023-09-30 | OC
3 | Proposed Site List (V1) | 2023-07-14 | 2023-07-14 | DTP
2 | Proposed site list final (V2) | 2023-11-13 | 2023-11-13 | DTP
3 | Agreement with Depts executed | 2023-08-04 | 2024-03-01 | DTP
3 | Agreement with LGAs executed | 2023-08-04 | 2024-06-01 | DTP
3 | Agreement with Private Owners | 2023-08-04 | 2025-01-01 | DTP
3 | PnR/W Market Engagement Strategy Approved | 2023-10-01 | 2024-01-31 | DTP
2 | Transport Hub Concept of Operations | 2023-10-01 | 2024-03-31 | DTP
2 | Transport Hub Service Model | 2023-10-01 | 2024-06-30 | DTP
2 | Transport Hub Service Plan | 2023-10-01 | 2024-06-30 | DTP
3 | Confirm Transport Hubs in games cities | 2023-03-31 | 2023-09-30 | DTP
3 | Identify Civil Works required | 2023-10-01 | 2024-06-30 | DTP
2 | Active Transport Strategy | 2023-10-01 | 2024-03-31 | DTP
3 | Identify Active Transport pathways (V1) | 2023-04-01 | 2023-12-31 | DTP
TRT - Road Network & Traffic Management
3 | Games Route Network (GRN) Specification v2 | 2023-09-01 | 2023-11-30 | DTP
2 | GRN Strategy Concept of Operations | 2023-05-01 | 2023-10-31 | DTP
3 | GRN and highway network modelling/journey time modelling (V2) | 2023-12-01 | 2024-02-28 | DTP
3 | Spectator Route Network (SRN) Specification v2 | 2023-09-01 | 2023-11-30 | DTP
2 | SRN Strategy Concept of Operations | 2023-05-01 | 2023-10-31 | DTP
3 | SRN and highway network modelling/journey time modelling (V2) | 2023-12-01 | 2024-02-28 | DTP
2 | SRN and highway network modelling/journey time modelling (V4 final) | 2023-12-01 | 2025-12-15 | DTP
2 | Local Area Traffic Management and Parking (LATMP) Strategy | 2023-10-01 | 2024-06-30 | DTP
3 | LATMP Operator Market Engagement Strategy Approved | 2023-09-30 | 2024-01-15 | DTP
3 | LATMP requirements gathering V1 | 2023-12-01 | 2023-12-15 | DTP
2 | Permit approvals received - pre games times | 2023-09-01 | 2026-03-09 | DTP
2 | Permit approval process - live changes during games times | 2023-09-01 | 2026-03-31 | DTP
TCE - Comms & Engagement
2 | Transport C&E Strategy | 2023-04-01 | 2023-12-15 | xx
2 | Journey Planner Strategy | 2023-08-01 | 2023-12-15 | DTP/OC
Note on D16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Seems late (Dec?); check with Angela
Note on B19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Find out from Ingrid - do we need to align to another accessibility strategy?
Note on D19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Aligns with VOP
Note on D56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reflects end of process and notification to parties based on go to market finished before Metro Bus EOI going out to market no earlier than 19 July.
Note on B66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Comes from VOP
Note on B67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Service plans
Note on B73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Where do these fit with the other service model and plans? Check with Angela
Note on B75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will need to work with other OC FA's
Note on B78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AG - Can I get clarity on this milestone please.
Note on B79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AG - Can I get further information on this milestone. Thanks.
Note on B83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What's the difference between this and the plan? Reply: AG - I dont think we need a model if we have a concept of ops
Note on B84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What does this need to align with? Civil works, overlay, LATMP, SRN
Note on B88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Already happening as part of VOP1 Reply: Will need to validate with councils
Note on D88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If this is part of VOP 1, can this be done by Dec 23? Dependency on last mile
Note on B98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AG - LATMP strategy is in advance of the market engagement. Reply: Can we align to GRN?